## Bug Status
# | Tracker | Component Name | Status | Priority | Subject | Comment
1684 | Bug | WALLET(KonaMoney) | Fixed | High - 높음 | after register new id, I can't log in. | TESTED PASS AND COMMENTED
1673 | Bug | WALLET(KonaMoney) | Fixed | Normal - 보통 | For unstable wifi connection wallet got crash | TESTED PASS AND COMMENTED
1669 | Bug | WALLET(KonaMoney) | Fixed | Normal - 보통 | when konamoney app started in memory full situation, it has problem that is pending. | TESTED PASS AND COMMENTED
1638 | Bug | CIS, CMS, MAP, PSM, WALLET(KonaMoney) | Fixed | High - 높음 | No notification is shown that the gift card issue was failed | TESTED FAIL AND COMMENTED
1633 | Bug | PSM, WALLET(KonaMoney) | Fixed | Normal - 보통 | [Set2] abnormal option card deletion and 0 cards | UNABLE TO REPRODUCE
1605 | Bug | MAP, PSM, WALLET(KonaPay) | Fixed | High - 높음 | PSM support single transaction ID for multiple card recharge purpose | NOT IN TEST SCOPE
1575 | Bug | MAP, WALLET(KonaMoney) | Fixed | Normal - 보통 | Card Activation Fails due to card Socket Timeout Exception | ARIF WILL CHECK
1541 | Feature | WALLET(KonaMoney) | Fixed | Normal - 보통 | purchase option card | TESTED PASS AND COMMENTED
1494 | Bug | WALLET(KonaMoney) | Fixed | Normal - 보통 | [SET1] mismatched nickname range. | UNABLE TO TEST
1475 | Bug | PSM-UI, WALLET(KonaMoney) | Fixed | Low - 낮음 | Showing gap between two cards into card list in wallet dashboard | TESTED PASS AND COMMENTED
1423 | Bug | WALLET(KonaMoney) | Fixed | Blocker - 즉시 | [Set1] Deletable basic card | TESTED PASS AND COMMENTED
1390 | Feature | MAP, WALLET(KonaMoney), WALLET(KonaPay) | Fixed | Normal - 보통 | Dynamic White box file distribution from server | NOT IN TEST SCOPE
1378 | Bug | WALLET(KonaMoney) | Fixed | Low - 낮음 | The toast message showed when wallet is crashed has a little grammatical error | TESTED PASS AND COMMENTED
1242 | Bug | PSM | Fixed | High - 높음 | Zero(0) balanced gift card received when sender cancelled and receiver receiveed at the same time | TESTED PASS AND COMMENTED
1224 | Feature | MAP, PP, WALLET(KonaMoney) | Fixed | Normal - 보통 | Notify wallet after successful transaction ( In-store, online payment) | ARIF WILL CHECK
1219 | Bug | WALLET(KonaMoney) | Fixed | Normal - 보통 | Refresh unused notification screen after activating service. | TESTED PASS AND COMMENTED
1165 | Bug | WALLET(KonaMoney) | Fixed | High - 높음 | Wallet can not delete or refund a option card immediately after a transaction. | TRANSACTION NOT POSSIBLE AT KSL
999 | Bug | WALLET(KonaMoney) | Fixed | Normal - 보통 | 카드거래내역 순서 오류 (Transaction Log order is wrong) | HQ
991 | Bug | WALLET(KonaMoney) | Fixed | Normal - 보통 | 충전 취소 중복요청시 앱 죽음 | HQ
990 | Bug | WALLET(KonaMoney) | Fixed | Normal - 보통 | 옵션카드 삭제 | HQ
986 | Bug | WALLET(KonaMoney) | Fixed | Normal - 보통 | 베이직카드 충전 한도 오류 | HQ
984 | Bug | WALLET(KonaMoney) | Fixed | Normal - 보통 | 회원 탈퇴 오류 | HQ
982 | Bug | WALLET(KonaMoney) | Fixed | Normal - 보통 | 회원가입시 닉네임 길이 오류(Nickname length error during registration) | HQ
905 | Bug | WALLET(KonaMoney) | Fixed | Normal - 보통 | [v0.50.00] , Auth ID and Code Error for resetting the password, Galaxy Note Edge(~4/8) | HQ

## Hot Cases
Case | Priority | Status | Comment
Register user with e-mail authentication mode(Check whether system taking duplicate mail address/phone-no or not, send/resend auth code is working, expiry of previous auth code, duration of an auth code, mismatch password detect) | P0 | Passed | SMS checking will be done by Arif
Register user with mix authentication mode (check that you are getting e-mail/msg properly and also their format is proper both in korean/english format) | P0 | Passed | Sms checking will be done by Arif
Check wallet initialize and observer all server calls during initialization to basic card download completion | P0 | Passed
Check whether basic card recharge is working through KFTC & KSNET | P0 | Passed
Purchase rechargeable/refundable/disposable/non-rechargeable option card with minimum & maximum balance (Check whether wallet prompt you to recharge basic card while you are trying to purchase an option card with insufficient balance in basic card) | P0 | Passed
Recharge option card with basic card | P0 | Passed
In-store transaction with both basic card & option card (check with sufficient value, insufficient value, try to do partial payment of a disposable card) | P0
Cancel recharge within due date/canccel in-store payment | P0
Delete option card and check whether the balance is refunded to basic card or not | P0 | Passed
Send/receive/recover/decline/accept/cancel gift | P0 | Passed | Could not test decline since gift card expire wasn't tested. The others are tested.
Check the gift details whether it is in appropriate format, also check the gift received msg & msg format in receiver mobile | P0 | Passed
Check gift expiry & recovery timing is synchronized with KonaMoney Gift policy and working accordingly | P1
Check whether received gift card is deleteable and its amount is refunded to basic card | P0 | Passed
Delete user account | P0 | Partially tested | Tested untill the card is refund reuested state, till that part wallet is working correctly.
Check whether user can delete account while having balance in any card or any gift in wait status | P0 | Partially tested | Need additional time for this since the card stays at Refund Request state
Re-registration with same e-mail/phone no and check resend/send auth code properly working, getting email/msg and also in right format | P0 | Partially tested | Need additional time for this since the card stays at Refund Request state
Change device | P0 | UNABLE TO TEST | Blocker issue in server, QRCode is not generating.
check resend/send auth code properly working, getting email/msg and also in right format while changing device | P0 | UNABLE TO TEST | Blocker issue in server, QRCode is not generating.
check that User has all the cards after device changing with proper balance and card status | P0 | UNABLE TO TEST | Blocker issue in server, QRCode is not generating.
All types of transaction/cancel transaction is working after device change | P0
Check all sending and receiving gift status after device change and whether gift is in wait status is recovered or not after changing device | P0
Suspend and resume wallet and check status of user and cards | P0
register refund account | P0
Check whether refund balance is working or not | P0
Check refund fee calculation/discount fee calculation is working as per service definition | P1
Check whether user can change password and send/resend auth code is working properly, also getting msg/e-mail and their format both in english and korean | P0
Check whether you are notified for extend expiry date, 7 days before the expiration | P0
Check that you can extend expiry date of your card | P0
Check expiry date of a card which has been send to a user as a gift | P1
Check whether you can send a gift which expiry date will be less than the recovery date | P1
Check transaction log for any specific card | P1
Check real name registration is working or not and you are getting its benefits properly | P1
Check autologin is working or not | P1
changing nick name/refund account | P1